## Corporate Risk Register
CYBERSECURITY RISK REGISTER FOR BUE
|  |  |  | BEFORE CONTROLS |  |  |  | AFTER CONTROLS
RISK ID NO. | RISK DESCRIPTION | IMPACT DESCRIPTION | RECURRENCE | IMPACT LEVEL | PROBABILITY LEVEL | PRIORITY LEVEL | What controls already exist that can address the risk? | IMPACT LEVEL | PROBABILITY LEVEL | PRIORITY LEVEL | DOCUMENTATION | OWNER | TARGET CLOSING DATE | STATUS | DATE CLOSED | KEYS
| Give a brief summary of the risk. | What will happen if the risk is not mitigated or eliminated? | Is it ongoing or only one time? | Rate 1 (LOW) to 5 (HIGH) | Rate 1 (LOW) to 5 (HIGH) | (IMPACT X PROBABILITY) Address the highest first. | If the risk can be eliminated or mitigated by existing processes, list them here. | Rate 1 (LOW) to 5 (HIGH) | Rate 1 (LOW) to 5 (HIGH) | (IMPACT X PROBABILITY) Address the highest first. | What are the key documents and processes related to the risk? | Who's responsible? | 00/00/00 | OPEN or CLOSED | 00/00/00 | RECURRENCE | LEVEL | STATUS
1 | Unauthorized access to sensitive data or systems by users from other groups | Data breach, compliance violations, disruption of operations | ONGOING | 4 | 3 | 12 | Identity and Access Management (IAM), Network Segmentation, Multi-Factor Authentication (MFA) | 2 | 2 | 4 | BUE IT Security Policies, Access Control Procedures | IT Security Manager | 2024-06-30 | OPEN |  | ONGOING | 1 | OPEN
2 | Malware infection leading to data loss or system downtime | Data corruption, productivity loss, remediation costs | ONGOING | 5 | 4 | 20 | Security Awareness Training, Endpoint Protection, Incident Response Plan | 3 | 3 | 9 | BUE IT Security Awareness Training Materials, Malware Incident Response Plan | IT Operations Manager | 2024-09-30 | OPEN |  | ONE TIME | 2 | CLOSED
3 | Phishing attack resulting in credential compromise | Unauthorized access, data breach, financial loss | ONGOING | 4 | 4 | 16 | Email Security Controls, Security Awareness Training, Incident Response Plan | 3 | 2 | 6 | BUE Email Security Guidelines, Phishing Simulation Exercise Reports | Information Security Officer | 2024-07-31 | OPEN |  |  | 3
4 | Insider threat - malicious or accidental data exposure | Reputational damage, legal implications, financial loss | ONE TIME | 5 | 2 | 10 | Data Encryption, Access Monitoring, Physical Security Controls | 3 | 1 | 3 | BUE Data Classification and Encryption Policy, Access Logs, CCTV Footage | HR Manager, IT Security Manager | 2024-12-31 | OPEN |  |  | 4
5 | Distributed Denial of Service (DDoS) attack disrupting online services | Service outages, revenue loss, customer dissatisfaction | ONGOING | 4 | 3 | 12 | Web Application Firewall (WAF), Next-Generation Firewall (NGFW), Incident Response Plan | 2 | 2 | 4 | BUE DDoS Mitigation Procedures, WAF/NGFW Logs | Network Operations Manager | 2024-08-31 | OPEN |  |  | 5
6 | Ransomware attack encrypting critical data and systems | Data loss, operational disruption, ransom payment costs | ONE TIME | 5 | 3 | 15 | Network Segmentation, Backup and Disaster Recovery, Incident Response Plan | 3 | 2 | 6 | BUE Backup and Recovery Procedures, Ransomware Incident Response Plan | IT Operations Manager, IT Security Manager | 2024-10-31 | OPEN
7 | Vulnerable software or system misconfigurations | Exploitation by attackers, data breaches, compliance violations | ONGOING | 4 | 4 | 16 | Vulnerability Management, Patch Management, Configuration Baselines | 2 | 2 | 4 | BUE Vulnerability Management Procedures, Configuration Standards | IT Operations Manager | 2024-07-31 | OPEN
8 | Unauthorized physical access to IT facilities | Theft of equipment, data breaches, sabotage | ONGOING | 4 | 2 | 8 | Physical Security Controls (CCTV, Access Controls, Guards) | 2 | 1 | 2 | BUE Physical Security Policies, Access Logs, CCTV Footage | Facilities Manager, IT Security Manager | 2024-09-30 | OPEN
9 | Lack of security awareness among users | Increased risk of successful attacks, compliance violations | ONGOING | 3 | 4 | 12 | Security Awareness Training Program | 2 | 2 | 4 | BUE Security Awareness Training Materials, Training Completion Records | Information Security Officer | 2024-06-30 | OPEN
10 | Inadequate incident response and recovery capabilities | Prolonged service outages, data loss, regulatory penalties | ONGOING | 4 | 3 | 12 | Incident Response Plan, Backup and Disaster Recovery | 2 | 2 | 4 | BUE Incident Response Plan, Backup and Recovery Procedure | IT Operations Manager, IT Security Manager | 2024-08-31 | OPEN
11 | Unauthorized remote access to university resources | Data breaches, system misuse, compliance violations | ONGOING | 4 | 3 | 12 | Secure Remote Access Control, Multi-Factor Authentication (MFA) | 2 | 2 | 4 | BUE Remote Access Policies, MFA Implementation Guide | IT Security Manager | 2024-07-31 | OPEN
12 | Lack of visibility into security events and threats | Delayed threat detection, ineffective incident response | ONGOING | 3 | 4 | 12 | Security Information and Event Management (SIEM) | 2 | 2 | 4 | BUE SIEM Implementation Guide, SIEM Logs and Alerts | Security Operations Center (SOC) Manager | 2024-09-30 | OPEN
13 | Sensitive data exposure during transmission | Data breaches, compliance violations, reputational damage | ONGOING | 4 | 3 | 12 | Data Encryption, Secure Communication Protocols | 2 | 2 | 4 | BUE Data Encryption Standards, Network Security Policies | IT Security Manager | 2024-08-31 | OPEN
14 | Unauthorized modification or deletion of critical data | Data integrity issues, operational disruption, compliance violations | ONGOING | 4 | 3 | 12 | Access Controls, Change Management, Backup and Recovery | 2 | 2 | 4 | BUE Access Control Policies, Change Management Procedures, Backup Logs | IT Operations Manager, IT Security Manager | 2024-10-31 | OPEN

## Scale
RISK REGISTER SCALE
P R O B A B I L I T Y | 5 | 5 | 10 | 15 | 20 | 25
| 4 | 4 | 8 | 12 | 16 | 20
| 3 | 3 | 6 | 9 | 12 | 15
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 | 2 | 3 | 4 | 5
|  | 1 | 2 | 3 | 4 | 5
I M P A C T